## Master Question Tracker
SEI Data Cloud (Azure) — Pricing Gaps & Risk Question Tracker
BBH Capital Partners Technology ¦ SWP Migration Program ¦ Prepared for David / CTO Review
# | Category | Question | Why It Matters | Pricing Impact | Est. $ Impact | Risk Level | Probability | BBH Action Required | SEI Owner | Status
PRICING STRUCTURE
1 | Pricing Structure | Is the $150K production setup fee a fixed price or estimate — what triggers overruns? | BBH cannot budget accurately if the fee is variable | Directly inflates one-time cost beyond $389K | $50K–$150K+ | Critical | High | Demand fixed-price SOW before signing | Commercial Lead | Open
2 | Pricing Structure | Why does Test Data Replication bill yearly ($9K) while all other test items bill monthly? | Creates lump-sum cash outflow misaligned with BBH monthly opex cycle | Cash flow timing mismatch; budget planning disruption | $9K lump sum | Medium | Certain | Request monthly billing alignment in negotiation | Commercial Lead | Open
3 | Pricing Structure | Is there a multi-year discount if BBH commits to 3–5 years upfront? | Year 1 cost is ~$986K — even 10% discount saves ~$60K/yr | Reduces total contract value significantly | $60K–$100K/yr | High | Medium | Negotiate multi-year pricing before signing | Commercial Lead | Open
4 | Pricing Structure | Are taxes, Azure marketplace fees, or duties included or added on top? | Hidden surcharges can add 5–15% to headline pricing | Inflates total cost of ownership materially | $30K–$80K/yr | High | Medium | Confirm all-in pricing in contract schedule | Legal / Finance | Open
5 | Pricing Structure | Is there an annual price escalation clause — what is the cap? | Recurring fees of $31K/month could increase at renewal | Compounds annually — 5% escalation = $18K/yr extra by Year 3 | $18K–$55K/yr | High | Medium | Cap escalation at CPI or 3% in contract | Legal | Open
6 | Pricing Structure | What is the payment milestone schedule for the $389K one-time fees? | Large upfront payment could conflict with BBH fiscal year budget cycles | Budget approval may require phased payment structure | $389K timing | Medium | Medium | Request milestone-based payment tied to deliverables | Finance | Open
SNOWFLAKE COMPUTE
7 | Snowflake Compute | Is the $7/hr per warehouse or per concurrent user session? | Multiple BBH users running reports simultaneously could multiply costs | Could 5x stated compute cost during peak usage | $50K–$120K/yr variance | Critical | High | Clarify billing unit; request concurrent user model | Technical Lead | Open
8 | Snowflake Compute | Is there a monthly hard cap on Snowflake compute spend? | No cap = open-ended financial liability on every invoice | Worst case: 24/7 compute = $60K/yr per environment | $60K–$120K uncapped | Critical | High | Contractually cap monthly compute; require alerts | Commercial Lead | Open
9 | Snowflake Compute | Who controls warehouse sizing — can SEI upgrade size without BBH approval? | Larger warehouse = higher $/hr — BBH loses cost control | Auto-upgrade from S→M doubles compute cost | 2x compute cost | Critical | Medium | Require BBH written approval for warehouse size changes | Legal | Open
10 | Snowflake Compute | Are SEI internal maintenance jobs billed against BBH's compute? | BBH should not pay for SEI's operational overhead | Invisible cost leakage — no line-item visibility | $5K–$20K/yr | High | Medium | Require compute isolation — BBH workloads only | Technical Lead | Open
11 | Snowflake Compute | What is the average monthly compute spend for a comparable client? | Benchmarks real-world cost vs $7/hr theoretical estimate | Informs realistic budget planning beyond base fees | Unknown — need data | High | Medium | Request 3 comparable client compute spend profiles | Commercial Lead | Open
12 | Snowflake Compute | Is compute billed per-second or rounded up to the full hour? | Per-second is significantly cheaper for short burst queries | Could reduce compute costs 30–50% if per-second | $15K–$30K/yr saving | Medium | Medium | Confirm billing granularity in pricing schedule | Commercial Lead | Open
13 | Snowflake Compute | During migration UAT — do both environments run simultaneously at full compute? | Peak period: Production validation + Test parallel run = double compute burn | Migration phase worst-case compute spike | $10K–$20K extra | High | Certain | Get migration phase compute estimate from SEI | Program Manager | Open
DATA REPLICATION
14 | Data Replication | What is the pricing tier above 15K accounts — is there a published rate card? | BBH Capital Partners growth may exceed 15K account threshold | Unplanned overage could trigger full contract renegotiation | Unknown — material | Critical | Medium | Obtain tiered pricing schedule up to 50K accounts | Commercial Lead | Open
15 | Data Replication | Are historical data backfill loads included in the $150K or billed separately? | Initial migration requires loading years of historical data — a large one-time compute event | Could add $20K–$50K to one-time cost not in current pricing | $20K–$50K | High | High | Confirm scope of one-time fee covers historical load | Technical Lead | Open
16 | Data Replication | Is there a data volume (GB/TB) limit in addition to the 15K account limit? | High-volume accounts (hedge funds, family offices) may have disproportionate data | Volume overage could trigger surcharge outside account pricing | Unknown | High | Medium | Request data volume policy and overage rates | Technical Lead | Open
17 | Data Replication | Who pays for replication retry compute when BBH sends a bad data file? | Data quality issues are common during migration — retries are inevitable | Accumulated retry costs could be significant during migration | $5K–$15K | Medium | High | Define retry cost responsibility in SLA schedule | Legal | Open
18 | Data Replication | What is the replication latency guarantee — what SLA breach looks like? | Stale data in SEI SDV = incorrect client reporting = NYDFS exposure | No SLA credit for stale data = BBH bears regulatory risk | Regulatory fine risk | Critical | Medium | Define latency SLA with credits for breach | Legal | Open
EVENT HUB
19 | Event Hub | What is the max events/sec guaranteed at $6,750/month — is there a throughput limit? | Month-end and quarter-end event spikes could breach throughput limits | Throttled events = processing delays = client reporting errors | Service disruption risk | High | Medium | Get guaranteed throughput SPS in contract | Technical Lead | Open
20 | Event Hub | Is the Event Hub dedicated to BBH or shared across multiple SEI clients? | Shared infrastructure means noisy-neighbour risk — another client's spike affects BBH | Performance degradation with no recourse | Service risk | High | Medium | Require dedicated Event Hub tier for BBH | Technical Lead | Open
21 | Event Hub | What is event retention period — can BBH replay events for reconciliation? | Reconciliation after NYDFS audit or client dispute requires historical event replay | If retention is <7 days BBH needs supplementary event store | $10K–$30K build cost | High | Medium | Require minimum 30-day retention for NYDFS compliance | Legal / Compliance | Open
22 | Event Hub | Are there additional fees if BBH event volume spikes at month-end? | Month-end = trade settlement + fee accrual + position reconciliation all at once | Unplanned overage charge at month-end every month | $2K–$10K/month | Medium | High | Define burst capacity policy and cost cap | Commercial Lead | Open
SDV DATA VISION
23 | SDV Data Vision | How many concurrent users are included in the $12,335/month SDV fee? | If BBH has 50+ RM users all running reports simultaneously — is that included? | Per-user licensing on top could double SDV cost | $50K–$100K/yr | Critical | Medium | Request named-user vs concurrent-user pricing model | Commercial Lead | Open
24 | SDV Data Vision | Are NYDFS-required regulatory reports included or separate modules? | Hema's compliance team needs specific NYDFS Part 500 reporting outputs | Regulatory report modules could add $20K–$50K/yr | $20K–$50K/yr | Critical | Medium | Get full module catalogue with pricing | Technical Lead | Open
25 | SDV Data Vision | What is the cost of custom report development beyond standard templates? | BBH has bespoke reporting requirements for Capital Partners clients | Professional services fees for customization not in baseline pricing | $50K–$200K | High | High | Define custom development rate card upfront | Commercial Lead | Open
26 | SDV Data Vision | Is there an API for programmatic data extract from SDV — and is it included? | BBH's Airflow pipelines may need to pull SDV data for downstream systems | API access may require premium tier adding $10K–$30K/yr | $10K–$30K/yr | High | Medium | Confirm API access tier and cost | Technical Lead | Open
SECURITY & COMPLIANCE
27 | Security & Compliance | Is production client data masked in the Test environment? | Unmasked PII in test = NYDFS Part 500 violation — significant regulatory exposure | Retroactive masking implementation cost if not included | Regulatory fine risk | Critical | High | Require data masking confirmation in security schedule | Legal / Compliance | Open
28 | Security & Compliance | Are BBH's Azure Key Vault / BYOK encryption keys included or extra? | BBH InfoSec likely requires control over their own encryption keys | BYOK may add $10K–$25K/yr in Azure Key Vault premium fees | $10K–$25K/yr | High | Medium | Confirm encryption key ownership in security schedule | InfoSec | Open
29 | Security & Compliance | Does SEI have SOC 2 Type II covering the Azure Data Cloud specifically? | BBH's third-party risk management process requires SOC 2 evidence | Without SOC 2 BBH cannot onboard SEI as a NYDFS-approved vendor | Vendor onboarding blocker | Critical | Medium | Request SOC 2 Type II report before contract signing | Compliance / Hema | Open
30 | Security & Compliance | Is Azure Private Link used — or does BBH data traverse public internet? | Data in transit over public internet = NYDFS Part 500 encryption requirement | Private Link setup may require premium Azure networking fees | $5K–$15K/yr | High | Medium | Confirm network path and private connectivity | InfoSec | Open
31 | Security & Compliance | Are NYDFS audit log retention requirements (6 years) covered in baseline? | NYDFS requires 6-year audit trail — standard cloud log retention is 30–90 days | Extended log retention in Azure Log Analytics = significant storage cost | $10K–$30K/yr | Critical | High | Confirm log retention policy and cost for 6-year NYDFS requirement | Legal / Compliance | Open
SLA & SUPPORT
32 | SLA & Support | What uptime SLA applies — and are SLA credits offered for breach? | BBH pays $31K/month regardless — no credits = SEI has no downtime incentive | Client reporting failure during NYDFS review = regulatory exposure | Regulatory / reputational | Critical | Medium | Require 99.9% SLA with meaningful credit schedule | Legal | Open
33 | SLA & Support | What is P1 incident response time for full platform outage? | If SDV goes down during client statement cycle — what is SEI's commitment? | No committed response time = uncontrolled client impact | Service disruption | High | Medium | Define P1 = 15-min response, 2-hour resolution in contract | Legal | Open
34 | SLA & Support | Is a dedicated Technical Account Manager included or an add-on? | During migration BBH needs a single SEI point of contact — not a ticket queue | Dedicated TAM typically adds $25K–$50K/yr if not included | $25K–$50K/yr | High | Medium | Require dedicated TAM in baseline contract | Commercial Lead | Open
35 | SLA & Support | Are planned maintenance windows excluded from uptime SLA calculation? | If SEI counts maintenance as uptime exclusion — real availability could be 97–98% | SLA appears strong but actual availability is materially lower | Misleading SLA | Medium | High | Define maximum monthly maintenance window allowance | Legal | Open
IMPLEMENTATION
36 | Implementation | Is there a detailed SOW with milestones and acceptance criteria for the $389K? | Without SOW BBH has no contractual recourse if SEI underdelivers | $389K paid with no enforceable deliverables = pure risk | $389K at risk | Critical | High | Require SOW before any payment | Legal / Program Manager | Open
37 | Implementation | Does the $389K include Airflow-to-Azure integration connectors? | BBH's OpenShift Airflow pipelines must connect to SEI Azure — who builds the bridge? | If not included BBH must fund and build integration internally | $50K–$100K | Critical | High | Define integration responsibility in SOW explicitly | Technical Lead / Andrew | Open
38 | Implementation | What is SEI's committed go-live timeline — and are there delay penalties? | SWP migration is on a regulatory timeline — delays have NYDFS implications | No penalty clause = SEI has no incentive to meet BBH's timeline | Program timeline risk | High | Medium | Define milestone dates with financial penalties for delay | Legal / Program Manager | Open
39 | Implementation | Does the 4-day Technical Overview cover BBH-specific configuration or generic? | Generic training is insufficient for BBH's bespoke Capital Partners data model | BBH may need additional paid professional services post-training | $30K–$80K | High | High | Define scope of training in SOW — BBH specific vs generic | Program Manager | Open
40 | Implementation | Is there a formal data migration runbook SEI provides for AddVantage/STAR cutover? | BBH is migrating ~2,500 legacy jobs — SEI guidance on migration sequencing is critical | Without runbook BBH bears full migration design risk | Migration failure risk | Critical | High | Request SEI migration methodology documentation before signing | Technical Lead | Open
CONTRACT & EXIT
41 | Contract & Exit | Is the $389K one-time fee fully refundable if BBH exits within Year 1? | If SEI underperforms BBH cannot recover setup investment | Non-refundable $389K = lock-in from day one | $389K stranded cost | Critical | Medium | Negotiate partial refund schedule tied to milestones | Legal | Open
42 | Contract & Exit | In what format and timeframe is BBH's data returned upon termination? | Snowflake-native format may not be compatible with BBH's Oracle stack | Data migration cost to rebuild from SEI export = $100K+ | $100K+ exit cost | Critical | Medium | Define data return format (CSV/Parquet) and 30-day SLA | Legal | Open
43 | Contract & Exit | If SEI is acquired — does BBH's contract auto-transfer on same terms? | SEI acquisition could change pricing, support model, or platform roadmap | BBH loses negotiated protections under new ownership | Contractual risk | High | Low | Insert change-of-control clause protecting BBH terms | Legal | Open
44 | Contract & Exit | What is the minimum notice period for termination — 30, 60, or 90 days? | Short notice period = flexibility; long notice = extended cost exposure | Longer notice = paying for unwanted service during transition | $31K–$93K/month | Medium | Medium | Cap notice period at 30 days in contract | Legal | Open

## Cost Impact Summary
SEI Data Cloud — Financial Exposure Summary
Stated pricing vs. potential total cost exposure with identified gaps
STATED ANNUAL COST (from pricing sheet)
Component | Production | Test | Total Annual | Billing Type
Data Replication — Recurring | 144000 | 9000 | 137700 | Prod=Monthly / Test=Yearly
Event Hub — Recurring | 81000 | 56700 | 266436 | Monthly
SDV Data Vision — Recurring | 148020 | 118416 | 40320 | Monthly
Snowflake Compute (moderate est.) | 20160 | 20160 | 389000 | Usage-based $7/hr
One-Time Setup (amortised Y1) | 220000 | 169000 | 986456 | One-time
TOTAL STATED YEAR 1 COST | 613180 | 373276 | 1819912
IDENTIFIED PRICING GAPS — ADDITIONAL EXPOSURE
Risk / Gap | Low Estimate | High Estimate | Risk Level | Likelihood | Mitigation
Snowflake compute uncapped overage | 20000 | 120000 | Critical | High | Cap compute monthly; set alerts
Test environment permanent cost | 184116 | 184116 | Critical | Certain | Budget as recurring opex; negotiate reduced rate
Account ceiling overage (>15K) | 50000 | 200000 | Critical | Medium | Obtain tiered pricing schedule now
NYDFS regulatory reports (extra module) | 20000 | 50000 | Critical | High | Include in scope or budget separately
Production data in test (masking cost) | 15000 | 40000 | Critical | High | Require masking in baseline contract
Setup fee overrun (no SOW) | 50000 | 150000 | High | Medium | Fixed-price SOW before signing
Custom report development | 50000 | 200000 | High | High | Define custom dev rate card upfront
Airflow-to-Azure integration (BBH build) | 50000 | 100000 | High | High | Clarify in SOW — SEI or BBH responsibility
Azure egress fees | 10000 | 40000 | Medium | Medium | Confirm inclusion in baseline fee
Dedicated TAM add-on | 25000 | 50000 | High | Medium | Include TAM in baseline contract
BYOK / Azure Key Vault premium | 10000 | 25000 | High | Medium | Confirm encryption key ownership
Annual price escalation (5% yr 3) | 18000 | 55000 | High | Medium | Cap at CPI or 3% in contract
Exit data migration cost | 100000 | 300000 | High | Low | Define data return format in contract
Event Hub burst charges (month-end) | 5000 | 30000 | Medium | High | Define burst policy and cost cap
Extended log retention (NYDFS 6yr) | 10000 | 30000 | Critical | High | Confirm 6-year retention in baseline
TOTAL ADDITIONAL EXPOSURE | 617116 | 1574116
⚠️ WORST CASE YEAR 1 TOTAL (Stated + High Exposure) → =SUM(D6:D10)+C30

## Risk Matrix
SEI Data Cloud — Risk Prioritisation Matrix
# | Risk Description | Category | Risk Level | Probability | Financial Impact ($) | BBH Action | Due Before
1 | Snowflake compute uncapped — open financial liability | Compute | Critical | High | $20K–$120K/yr | Cap monthly compute; require alert thresholds | Contract signing
2 | No SOW for $389K one-time fee | Implementation | Critical | High | $389K at risk | Demand SOW with milestones before any payment | Contract signing
3 | Production data unmasked in Test environment | Compliance | Critical | High | Regulatory fine | Require data masking in security schedule | Contract signing
4 | NYDFS 6-year log retention not confirmed | Compliance | Critical | High | $10K–$30K/yr | Confirm retention policy; cost inclusion | Contract signing
5 | Account ceiling overage pricing unknown (>15K accounts) | Pricing | Critical | Medium | $50K–$200K | Obtain tiered rate card before signing | Contract signing
6 | NYDFS regulatory report modules not in baseline | Compliance | Critical | Medium | $20K–$50K/yr | Get full module catalogue with pricing | Contract signing
7 | No uptime SLA credits for downtime | SLA | Critical | Medium | Regulatory exposure | Define SLA credits in contract | Contract signing
8 | Test environment cost is permanent post go-live | Pricing | Critical | Certain | $184K/yr ongoing | Budget as permanent opex; negotiate reduced rate | Budget planning
9 | Airflow-to-Azure integration responsibility undefined | Implementation | High | High | $50K–$100K build | Define in SOW — SEI or BBH responsibility | SOW negotiation
10 | Historical backfill load not in $150K setup fee | Implementation | High | High | $20K–$50K extra | Confirm historical load scope in SOW | SOW negotiation
11 | Custom report development not in baseline | SDV | High | High | $50K–$200K | Define custom dev rate card upfront | Contract signing
12 | No go-live timeline penalty clause | Implementation | High | Medium | Program delay | Define milestone penalties for SEI delay | Contract signing
13 | No annual price escalation cap | Pricing | High | Medium | $18K–$55K/yr by Yr3 | Cap at CPI or 3% in contract | Contract signing
14 | Dedicated TAM not confirmed in baseline | Support | High | Medium | $25K–$50K/yr | Include TAM in baseline contract | Contract signing
15 | Snowflake warehouse sizing controlled by SEI | Compute | High | Medium | 2x compute cost | Require BBH written approval for size changes | Contract signing
16 | Event Hub shared across SEI clients (noisy neighbour) | Event Hub | High | Medium | Service degradation | Require dedicated Event Hub tier | Contract signing
17 | Azure BYOK / Key Vault not confirmed included | Security | High | Medium | $10K–$25K/yr | Confirm encryption ownership in security schedule | Contract signing
18 | SEI acquisition — contract protection unclear | Contract | High | Low | Full contract risk | Insert change-of-control clause | Contract signing
19 | Event Hub burst charges at month-end | Event Hub | Medium | High | $5K–$30K/month | Define burst policy and hard cap | Contract signing
20 | Azure egress fees not confirmed included | Infrastructure | Medium | Medium | $10K–$40K/yr | Confirm in all-in pricing schedule | Contract signing
21 | Test billing cycle mismatch (yearly vs monthly) | Pricing | Medium | Certain | Cash flow timing | Request monthly billing alignment | Contract signing
22 | Snowflake billed rounded-up hourly not per-second | Compute | Medium | Medium | $15K–$30K/yr | Confirm billing granularity | Contract signing
23 | Exit data return format not defined | Contract | Medium | Medium | $100K+ rebuild | Define return format and 30-day SLA | Contract signing
24 | Event Hub message retention <30 days | Event Hub | Medium | Medium | Build supplementary store | Require 30-day minimum retention | Contract signing
25 | Payment milestone schedule not defined for $389K | Pricing | Medium | Medium | Budget approval risk | Request milestone-based payment | Finance planning

## Pre-Sign-Off Checklist
SEI Data Cloud — Pre-Contract Sign-Off Checklist ¦ David / CTO Review
# | Must-Answer Question | Why Critical | Owner | Target Date | Status
1 | Obtain detailed SOW with milestones and acceptance criteria for the $389K | Without SOW BBH has no contractual protection on $389K | Legal / Program Mgr | Pre-signing | ⬜ Open
2 | Confirm Snowflake compute monthly hard cap with auto-alert thresholds | Open compute = open financial liability on every invoice | Commercial Lead | Pre-signing | ⬜ Open
3 | Confirm production data is masked in Test environment | Unmasked PII in test = NYDFS Part 500 violation | Compliance / Hema | Pre-signing | ⬜ Open
4 | Obtain SEI SOC 2 Type II report covering Azure Data Cloud | Required for NYDFS third-party risk management onboarding | Compliance / Hema | Pre-signing | ⬜ Open
5 | Confirm account overage pricing above 15K — get tiered rate card | Growth beyond 15K triggers unbudgeted renegotiation | Commercial Lead | Pre-signing | ⬜ Open
6 | Confirm NYDFS regulatory report modules are in scope | Compliance reports are non-negotiable — must be included or budgeted | Legal / Hema | Pre-signing | ⬜ Open
7 | Define uptime SLA with credit schedule for each component | $31K/month with no credits = no SEI downtime accountability | Legal | Pre-signing | ⬜ Open
8 | Define Airflow-to-Azure integration responsibility in SOW | If BBH builds it — $50K–$100K not in current budget | Technical Lead / Andrew | Pre-signing | ⬜ Open
9 | Confirm historical data backfill load is included in $150K setup | Large one-time compute event not in current budget estimate | Technical Lead | Pre-signing | ⬜ Open
10 | Confirm 6-year NYDFS audit log retention is included in baseline fee | 6-year retention is mandatory — not standard Azure default | Legal / Hema | Pre-signing | ⬜ Open
11 | Lock annual price escalation cap at CPI or 3% | Uncapped escalation compounds materially over 5-year term | Legal | Pre-signing | ⬜ Open
12 | Confirm Azure Private Link used — no public internet data transit | NYDFS Part 500 requires encryption in transit — Private Link preferred | InfoSec | Pre-signing | ⬜ Open
13 | Define go-live timeline with financial penalties for SEI delay | SWP migration is on regulatory timeline — delays have consequences | Program Manager | Pre-signing | ⬜ Open
14 | Define data return format and 30-day SLA for contract exit | Snowflake-native format unusable in BBH Oracle stack | Legal | Pre-signing | ⬜ Open
15 | Insert change-of-control clause protecting BBH terms on SEI acquisition | SEI M&A would otherwise void negotiated protections | Legal | Pre-signing | ⬜ Open